## Sheet1
| Checklist Item | Planned? | Authorisation | Completed? | Risks | Notes | Custom Field #1 | Custom Field #2 | Custom Field #3 | Custom Field #4 | Custom Field #5
P1 | Phase 1: Pre-Migration Planning
P1.1 | Have you assessed the viability of your migration with a pre-migration impact assessment?
P1.2 | Have you based project estimates on guesswork or a more accurate assessment?
P1.3 | Have you made the business and IT communities aware of the need for their involvement?
P1.4 | Have you formally agreed the security restrictions for your project?
P1.5 | Have you identified your key project resources and when they are required?
P1.6 | Have you determined the optimal project delivery structure?
P1.7 | Have you created a structured task workflow so each member will understand what tasks are expected and in which sequence?
P1.8 | Have you created the appropriate training documentation and designed a training plan?
P1.9 | Do you have a configuration management policy and the appropriate software in place?
P1.10 | Have you planned for a secure, collaborative working environment to be in place?
P1.11 | Have you created an agreed set of data migration policy documents?
P2 | Phase 2: Project Initiation
P2.1 | Have you created a stakeholder communication plan and stakeholder register?
P2.2 | Have you tweaked and published your project policies?
P2.3 | Have you created a high-level, first-cut project plan?
P2.4 | Have you created your standard project document templates?
P2.5 | Have you defined and formalised your 3rd Party supplier agreements and requirements?
P2.6 | Have you scheduled your next phase tasks adequately?
P2.7 | Have you resolved any security issues and gained approved access to the legacy datasets?
P2.8 | Have you defined the hardware and software requirements for the later phases?
P3 | Phase 3: Landscape Analysis
P3.1 | Have you created a detailed data dictionary?
P3.2 | Have you created a high-level source to target mapping specification?
P3.3 | Has the risk management process been shared with the team and are they continuously updating the risk register as issues are discovered?
P3.4 | Have you created a data quality management process and impact report?
P3.5 | Have you implemented Privacy Impact Assessment (for customer/contact datasets, GDPR related)
P3.6 | Have you created and shared a first-cut system retirement strategy?
P3.7 | Have you created conceptual/logical/physical and common models?
P3.8 | Have you refined your project estimates?
P4 | Phase 4: Solution Design
P4.1 | Have you created a detailed mapping design specification?
P4.2 | Have you created an interface design specification?
P4.3 | Have you created a data quality management specification?
P4.4 | Have you defined your production hardware requirements?
P4.5 | Have you agreed the service level agreements for the migration?
P5 | Phase 5: Build & Test
P5.1 | Has your build team documented the migration logic?
P5.2 | Have you tested the migration with a mirror of the live environment?
P5.3 | Have you developed a reconciliation testing strategy?
P5.4 | Have you defined your reporting strategy and associated technology?
P5.5 | Have you created a data migration fall-back policy?
P5.6 | Have you confirmed and planned your legacy decommission strategy?
P5.7 | Have you completed all relevant execution training?
P5.8 | Have you obtained sign-off for anticipated data quality levels in the target?
P5.9 | Have you defined the data migration execution strategy?
P5.10 | Have you created a gap-analysis process for measuring actual vs current progress?
P6 | Phase 6: Execute & Validate
P6.1 | Have you kept an accurate log of SLA progress?
P6.2 | Have you independently validated the migration?
P7 | Phase 7: Decommission & Monitor
P7.1 | Have you completed your system retirement validation?
P7.2 | Have you handed over ownership of the data quality management environment?